## Slide 1: ECS T&T Project - Weekly Status Report_10.11.2023

## Slide 2
Hexaware EXM
Activities – In Progress/ Completed
AskGenie Out of 292 Catalogs,216 reviewed (Batch 1 & 2) 29- WIP (Batch 3) 32 Not available for now. After 3 successful releases, 68 catalogues moved to production and 71 decommissioned. Next development will start after 25th Oct due to platform upgrade freeze. However, BA will continue working. Onboarding Journey The core group members and their team have started working on the agreed recommendations. Follow up sessions will be scheduled with stake holders on individual items. StationH to Work Vivo Migration After the kick of session, Started with 1st weekly project connect and a technical intro session. Followed by, 1 more weekly project call, 1 technical session and an internal connect on every Friday.
Upcoming Activities
AskGenie A tentative release for phase 4, will be after 28th Oct Sprint-11 Dev & UAT to be completed Targeting on completing the remaining catalogues are in work InProgress. Onboarding Journey Target date against the accepted recommendations to be finalized. Discussion will be done next week with the core group. StationH to Work Vivo Migration OneDrive access to be enabled for external file sharing. Requirement Gathering sessions to be conducted by WorkVivo team for Foundation Setup
Key Milestones | Status | Planned Dates |  | Revised End Date | % Completed
 |  | Start | End |  | 
Ask Genie Transformation |  | 27-Mar-23 | 3-Nov-23 |  | 97%
Onboarding Journey |  | 14-Feb-23 | TBD |  | 50%
StationH to Work Vivo Migration |  | 4-Oct-23 | TBD |  | 30%
Risk, Action, Issues & Dependencies
AskGenie : Flow of project details to AskGenie from BPS, Hexaware IT, Mobiquity are different. This is creating roadblock on consolidation of Catalog items. Interim Workaround: As the project go live is in Sep’2024, AskGenie team has tried to implement the interim workaround solution after converting the data in required format. The solution can be able to fulfill 90% of the data. Additional factors are being worked upon by the team, such as, scripting for location information etc.. Onboarding Journey : Target date on the accepted recommendations to be finalized.
Project Type | Employee Experience Management | Customer | Vinod Chandran | ECS Team | Parijit Nath Santhanalakkshmi Venkataramani Tanpreet Malhotra Sunit Sinha Ketaki Tapi Vaishnavi Barhate Himanshu Bhide
Report Date | 17-Oct-23 | Overall Progress | 100% |  | 
Project Manager | Murugan Bheeman | Go Live |  |  | 
Budget Hours |  | Utilized Hours |  |  | 
Project Phase | Execution |  |  |  | 
Delayed
Risk Of Delay
On Track
Completed
Project Status | 
Scope | Ask Genie Transformation Onboarding Journey StationH to WorkVivo Migration

## Slide 3
LSEG Joiner Mover and Leaver
Activities – In Progress/ Completed
Enhancements on New Joiner Request Form for LSEG and RFT Automation of New Joiner Request Form for LSEG Clarity Request Form - for LSEG and RFT Conversion request Form – not released yet in production Harmonization of Refinitiv data in ESM ServiceNow - for LSEG and RFT Hardware Request form - for LSEG and RFT VDI Request Form - for LSEG and RFT Leaver Journey- Hardware Handover Request Form Manager Action Request Form Custom notifications to leaver & Line manager Validate User Request Form Respective Dashboards for all above catalog items Restrict RFT ServiceNow catalogs(initially was not in our scope)
Upcoming Activities
Create customize notification to Line manager for LSEG/RFT New Joiners Leaver Enhancements Automate RFT New Joiner logic VDI Automation Conversion Request Form Enhancement on New Joiner and Leaver process to add CMDB to populate user assets Defect solution- custom notifications for potential LSEG & RFT leaver & Line manager
Key Milestones | Status | Planned Dates |  | Revised End Date | % Completed
 |  | Start | End |  | 
Discovery |  | 21-Aug-23 | 1-Sep-23 |  | 100%
Design |  | 1-Sep-23 | 8-Sep-23 |  | 100%
Implementation |  | 15-Sep-23 | 27-Sep-23 |  | 100%
Go Live |  | 1-Oct-23 | 1-Oct-23 |  | 100%
Risk, Action, Issues & Dependencies
Few upcoming activities are dependent upon ITSM release, which is planned for Nov, 2023
Project Type | Joiner Mover and Leave (JML) | Customer | Nivedhan Sandrakanthan | ECS Team | Upasna Pandita
Report Date | 17-Oct-23 | Overall Progress | 100% |  | 
Project Manager |  | Go Live | Multiple |  | 
Budget Hours |  | Utilized Hours |  |  | 
Project Phase | Execution |  |  |  | 
Delayed
Risk Of Delay
On Track
Completed
Project Status | 
Scope | JML Transformation

## Slide 4
LSEG Chatbot
Activities – In Progress/ Completed
Gathered the requirements from the stake holders, created user stories and amended them with the business for approvals. Shared the user stories with the development team and have those developed with daily discussions on the scrum call. Gathered the phase1 requirements and collated them onto confluence page. Took the user stories to the business on getting the DIF approvals post which the development were agreed upon. Follow up on the test case scenarios and capture the results. Attend meetings with the service design team on the workflow or design changes and apply them to the existing user stories. Frequent meetings with the QA team on workstream testing and clarifying their queries with the regards
Upcoming Activities
Key Milestones | Status | Planned Dates |  | Revised End Date | % Completed
 |  | Start | End |  | 
Discovery |  | 21-Aug-23 | 1-Sep-23 |  | 100%
Design |  | 1-Sep-23 | 8-Sep-23 |  | 100%
Implementation |  | 15-Sep-23 | 27-Sep-23 |  | 100%
Go Live |  | 1-Oct-23 | 1-Oct-23 |  | 100%
Risk, Action, Issues & Dependencies
Project Type | KoreAI Chatbot | Customer |  | ECS Team | Imran Haji
Report Date | 17-Oct-23 | Overall Progress | 100% |  | 
Project Manager |  | Go Live |  |  | 
Budget Hours |  | Utilized Hours |  |  | 
Project Phase | Execution |  |  |  | 
Delayed
Risk Of Delay
On Track
Completed
Project Status | 
Scope | Business Analysis activities

## Slide 5
TTC JML PoC
Activities – In Progress/ Completed
Upcoming Activities
Key Milestones | Status | Planned Dates |  | Revised End Date | % Completed
 |  | Start | End |  | 
Discovery |  | 21-Aug-23 | 1-Sep-23 |  | 100%
Design |  | 1-Sep-23 | 8-Sep-23 |  | 100%
Implementation |  | 15-Sep-23 | 27-Sep-23 |  | 100%
Go Live |  | 1-Oct-23 | 1-Oct-23 |  | 100%
Risk, Action, Issues & Dependencies
Project Type | Joiner Mover and Leave (JML) | Customer |  | ECS Team | Kanika Suyal
Report Date | 17-Oct-23 | Overall Progress | 100% |  | 
Project Manager |  | Go Live |  |  | 
Budget Hours |  | Utilized Hours |  |  | 
Project Phase | Execution |  |  |  | 
Delayed
Risk Of Delay
On Track
Completed
Project Status | 
Scope | Joiner Request form for three locations & one persona Mover Request form for three locations & one persona Leaver Request form for three locations & one persona